## Sheet1
Names | Tasks | weeks in each milestone | Due dates of each task | Milestones due dates | NOTES: Replace "Group member 1" with the student's first name, and repeat for all other group members
Andrae Taylor | Find project resources for AI chatbot using DeepSeek | week1: 5/14-5/20 |  | Milestone 1 on 5/28 @ 1:00pm | NOTES: Delete the 4th and 5th group members if your group only has 3 members
Bryce Lucas | Decide on structure of the website for DeepScan website |  |  |  | NOTES: For each task, you can include documentation, but remember that ALL group members must also have a technical contribution week-to-week
Aidan Chapman | Also deciding the structure of the website for our AI chatbot using DeepSeek |  |  |  | NOTES: Delete these 4 NOTES cells when you submit your template
Kole Micakaj | Finding tutrorials for DeepSeek AI
Michael Lafata | Find Tutorials for DeepSeek chatbot
Andrae Taylor | create wireframes for chatbot interactons and the resume feedback layout | week2: 5/21-5/27
Bryce Lucas | Set up the Github repository and initial project structures
Aidan Chapman | design the website schema for user resumes and job titles
Kole Micakaj | install and test DeepSeek model locally or in our dev enviornment
Michael Lafata | Create intial front end form for resume upload and job title input
Andrae Taylor | implementing input handling for job titles and resume files | week1: 5/28-6/3 |  | Milestone 2 on 6/18 @ 1:00pm
Bryce Lucas | Connect backend to DeepSeek AI and test basic functonality
Aidan Chapman | Develop API endpoints for uploading and retrieving resume data
Kole Micakaj | Begin building the logic to parse resume text and extract content
Michael Lafata | work on chatbot dialouge logic for tailoring advice on job titles
Andrae Taylor | Refine chatbot messages to match tone and clarity | week2: 6/4-6/10
Bryce Lucas | Enable saving and loading previous resume sessions
Aidan Chapman | Optimize prompt engineering for DeepSeek responses
Kole Micakaj | Integrate fallback/ error handling for bad inputs or unsupported files
Michael Lafata | Test chatbot UX on desktop and mobile viewports
Andrae Taylor | Conduct full system walkthrough and document user flow | week3: 6/11-6/17
Bryce Lucas | Fic bugs found in backend or chatbot logic during internal testing
Aidan Chapman | Write backend deployment instructions and setup docs
Kole Micakaj | Create test cases for resume parsing and chatbot behavior
Michael Lafata | prepare slides and demo material for milestone 2 presentation